## Product Backlog
Product Name: | Mav’s Animal Shelter Software (MASS) | [6 empty] | Complete Fields in Green!!!
Team ID:
| Team Member Name | [5 empty] | Initials | Student ID
Required | IKECHUKWUKA OFILI | [5 empty] | ICO | 1001862556
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 36 |  |  |  | Total | Total number of features (in column H)
1 | 32 | 4 |  |  | 1 | Total features left at the end of Sprint #1
2 | 25 | 7 |  |  | 2 | Total features left at the end of Sprint #2
3 | 20 | 5 |  |  | 3 | ...and so on
4 | 17 | 3
5 | 14 | 3
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
ANIMAL | 1 | 1 |  | 5 |  | Finished in Sprint 1 | User | Track the name, gender, and age for all animals | Keep track of guests at our shelter | Need enum for Gender and abstract Animal class with constructor, getters, and toString. Validate that age is not negative else throw an exception.
DOG | 2 | 1 |  | 8 |  | Finished in Sprint 1 | Staff | Create a new dog (or any other family of animals) | Track pets seeking good homes | Need Dog class that extends Animal along with DogBreed enum (may be any animal family, not necessarily Dog).
LANIM | 3 | 1 |  | 8 |  | Finished in Sprint 1 | Staff | Keep a list of animals | See what animals are available | Requires Shelter class with a shelter name and array list of animals. Need to be able to add an animal and access the available animals.
CAT | 4 | 1 |  | 5 |  | Finished in Sprint 1 | Staff | Create and list cats (or 2nd animal family) as well | Put 2nd pet type up for adoption | Very similar to 1st type of pets
MAINWIN | 5 | 2 |  | 3 |  | Finished in Sprint 2 | User | Display a main window with menu | Use the program more easily | Baseline Nim
TOOLBAR | 6 | 2 |  | 2 |  | Finished in Sprint 2 | User | Include a toolbar | Click buttons for actions | Baseline Nim; add 2 buttons for inserting the two animal families
ABOUT | 7 | 2 |  | 3 |  | Finished in Sprint 2 | User | Include an About dialog for toolbar icons (Help > About) | Avoid legal trouble | Baseline Nim; need icons for the two animal families; use YOUR name
EXIT | 8 | 2 |  | 2 |  | Finished in Sprint 2 | User | Exit the main program (File > Quit or x window control) | Quit reliably | Baseline Nim
DOGDIALOG | 9 | 2 |  | 13 |  | Finished in Sprint 2 | Staff | Use dialogs to create a new dog or 1st family (Animal > New Dog) | Track pets seeking good homes | May be a series of JOptionPane dialogs or a single unified dialog
CATDIALOG | 10 | 2 |  | 8 |  | Finished in Sprint 2 | Staff | Use dialogs to create a new cat or 2nd family (Animal > New Cat) | Track more pets seeking good homes | Similar to 1st
SHOWANIM | 11 | 2 |  | 5 |  | Finished in Sprint 2 | Staff | Display all animals in the main window (Animal > List Available) | See the beloved animals that are current guests of the shelter | Update after every Insert operation (Animal > List Available will be needed when clients are added in a later sprint). May be a label or similar widget in the data area of the main window
SAVE | 12 | 3 |  | 8 |  | Finished in Sprint 3 | Manager | Save the data to a default file (File > Save) | Persist our data through the years | Requires Animal.save(bw), Dog.save, Cat.save, Shelter.save; Shelter.filename with getter and setter, and Mass.onSaveClick
LOAD | 13 | 3 |  | 8 |  | Finished in Sprint 3 | Manager | Load the data from a default file (File > Open) | Persist our data through the years | Requires Animal.Animal(br), Dog.Dog, Cat.Cat, Shelter.Shelter and Mass.onOpenClick; dialog and logic for handling “dirty” data
NEW | 14 | 3 |  | 5 |  | Finished in Sprint 3 | Director | Create a new shelter (File > New) | Open additional shelters as needed | Requires Mass.onNewShelterClick
SAVEF | 15 | 3 |  | 5 |  | Finished in Sprint 3 | Director | Save the data to a specified file (File > Save As) | Backup or baseline a new shelter | Requires Mass.onSaveAsClick, Shelter.setFilename; adding JFileChooser
LOADF | 16 | 3 |  | 3 |  | Finished in Sprint 3 | Director | Load the data from a specified file (File > Open) | Work with multiple shelters | Requires adding JFileChooser
GENERIC | 17 | 4 |  | 13 |  | Finished in Sprint 4 | Staff | Refactor Add (Animal) dialogs into generic class and add at least one additional family of animals | Quickly add additional animal families to our guest list | Requires generic class for unified dialog to create new animal guests
CLIENT | 19 | 4 |  | 8 |  | Finished in Sprint 4 | Staff | Create a new client (Client > New) | Track candidate adopters | Requires Mass.onCreateClient; 1 dialog; class Client; Shelter.addClient and fields
LCLIENT | 20 | 4 |  | 5 |  | Finished in Sprint 4 | Client | List clients (Client > List) | See which clients are available | Requires Shelter.numClients and client; and Mass.onClientsList
ITER | 18 | 5 |  | 5 |  | Finished in Sprint 5 |  | Refactor to use iterators to access animals from Shelter | Practice iterators (well?) | Replace numAnimals and getAnimal with getAnimalIterator; update all users of those methods
ADOPT | 21 | 5 |  | 13 |  | Finished in Sprint 5 | Client | Adopt an animal (Client > Adopt Animal) | Adopt an animal! | Requires Shelter.adopted HashMap<Animal, Client>, new dialog
LADOPT | 22 | 5 |  | 8 |  | Finished in Sprint 5 | Staff | List adopted animals (Client > List Adopted and Animal > List Adopted) | See which client adopted which animal | Requires 1 dialog to select the client and 1 dialog to select the animal; Mass.onListAdoptedClick
Bonus Features
SCROLL | 23 |  | 15 | 8 | Bonus |  | Staff | Add scroll bars to the main window data area | Expand the shelter beyond the size of our monitors | Use a JScrollPane to hold your JLabel and set the policies you prefer
NANIM | 24 |  | 10 | 5 | Bonus |  | Client | Create new animals and / or clients during adoption | Simplify the adoption process | Add “New Client” and "New Animal" buttons to the Adoption dialog. After the client or animal has been added, refresh the JComboBoxes and resume the Adoption dialog with the new item pre-selected
PHOTO | 25 |  | 15 | 8 |  |  | Client | See photo and information about an available animal | Decide if it’s right for my family | Update existing animal selection dialog to accept image filename and store in Animal instance. Display image (perhaps as icon) when animal data is shown stand-alone. (If you can show the image in the main window list of animals, that's a much bigger bonus! This may require at least TRUETABLE.)
RETURN | 26 |  | 10 | 5 | Bonus |  | Client | Return pet, e.g., unable to keep in apartment | Easily handle unexpected challenges | Move Animal from the adoptions HashMap to the animals ArrayList, then remove the adoption pair from the adoptions HashMap
REMOVE | 27 |  | 5 | 3 |  |  | Staff | Remove animal from the available list, presumably for good | Deal with animal deaths or transfers | Create a formerAnimals ArrayList and support swaps to/from the animals ArrayList (a long-term form of "undo")
ANUNAVAIL | 28 |  | 10 | 5 | Bonus |  | Staff | Temporarily remove animal from the available list, for example if sick or in foster care | Deal with animals who are currently not available for adoption | Create an unavailableAnimals ArrayList and support swaps to/from the animals ArrayList (a long-term form of "undo") and (if REMOVE) the formerAnimals ArrayList
CLUNAVAIL | 29 |  | 10 | 5 | Bonus |  | Staff | Remove client from the list of those seeking adoptions | Deal with former clients and those who aren't interested right now | Create a formerClients ArrayList and support swaps to/from the clients ArrayList, to hold those who currently are not seeking adoptions
PROP | 30 |  | 15 | 8 | Bonus |  | Staff | Add File > Properties dialog | Check status of the shelter | Show shelter name, filename, number of animals available, unavailable, temporarily unavailable, and adopted (for features implemented); and number of clients
CLEDIT | 31 |  | 10 | 5 | Bonus |  | Staff | Edit client information | We can handle name and phone number changes | Select the client from a dialog, then load their information into the same dialog as used to create. On OK, update the client's information.
ANEDIT | 32 |  | 25 | 13 | Bonus |  | Staff | Edit animal information | We can handle changes to animal data | Select the animal from a dialog (up to 3 lists - available, unavailable, and former), then load their information into the same dialog as used to create. On OK, update the animal's information.
ANAGE | 33 |  | 25 | 13 |  |  | Staff | Replace Animal.age with Animal.birthday and calculate age | Animal ages are accurate | This adds a private field to Animal, and an age() method. Be sure to handle Open and Save/Save As changes that result. Displaying the birthday would be a nice touch, too.
PERCLIENT | 34 |  | 15 | 8 | Bonus |  | Staff | Select a client (current and former, if available) from a dialog, then list all their adopted Animals in main window | Focus on interactions with a specific client | This requires a JComboList or a JList to select the client, then search adoptions for pairs with that value and add the table to the data JLabel
TRUETABLE | 35 |  | 25 | 13 |  |  | Staff | Replace the JLabel as your main window data display with a true table | Better interaction with data | Use a JTable connected to an array of column headers and 2D array of data that is updated when updateDisplay is called.
LIVETABLE | 36 |  | 75 | 34 |  |  | Staff | Replace the non-interactive table as your main window data display with an interactive table | Even better interaction with data | Similar to TRUETABLE except connect the table directly to the shelter package, so that changes are instantly reflected. You may need tabs to switch views between animals and clients and the other various reports. Adding listeners to cells for editing animals or clients, for example, will result in even more bonus points being added.
Note on E54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If both ANUNAVAIL and CLUNAVAIL are implemented such that animals can freely move between all 3 lists, add 10 extra bonus points.

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2022-04-19 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-04-26
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 0
Day 1 Left | 0 | 0
Day 2 Left | 0 | 0
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | ITER
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2022-02-22 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-03-01
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2022-03-01 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-03-08
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2022-03-08 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-03-15
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2022-04-12 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-04-19
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Bonus Sprint Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2022-04-19 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-04-26
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 0
Day 1 Left | 0 | 0
Day 2 Left | 0 | 0
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | SCROLL
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84